## Assignment Usage
Weekly Calendar | All
Data
Task | Task 1 | Resources | Baseline Work | Work | Actual Work | Remaining Cumulative Work | Remaining Cumulative Actual Work | Baseline Remaining Cumulative Work
Project1 | Library | Khanh | 338 | 356 | 147 | 0 | 209 | 0
|  | Bao | 336 | 384 | 226 | 0 | 158 | 0
|  | Vi | 432 | 478 | 224.1 | 0 | 253.9 | 0
|  | Luong | 328 | 360 | 178.1 | 0 | 181.9 | 0
|  | Hung | 312 | 328 | 153.3 | 0 | 174.7 | 0
|  | FrontEnd;Server | 40 | 40 | 40 | 0 | 0 | 0
|  | Bakend;Server | 40 | 40 | 40 | 0 | 0 | 0
|  | Domain | 1 | 1 | 1 | 0 | 0 | 0
|  | Database | 75 | 88 | 88 | 0 | 0 | 0
|  | Hardware | 0 | 0 | 0 | 0 | 0 | 0
|  | Software | 0 | 0 | 0 | 0 | 0 | 0
| Library Total |  | 1902 | 2075 | 1097.5 | 0 | 977.5 | 0
Project1 Total |  |  | 1902 | 2075 | 1097.5 | 0 | 977.5 | 0
Grand Total |  |  | 1902 | 2075 | 1097.5 | 0 | 977.5 | 0